## Timelines
Key for Timelines
Foundational items (catalog, calendar) | Date
Meetings & Decisions | Date
Documentation | Date
SACSCOC Approval required? | Yes/No
SACSCOC Approval obtained? | Yes/No/NA
Implementation | Date
Module Leaders
Marketing Module | Name
Admissions & Administrative Services | Name
Academics Module | Name
Academic Student Support Services Module | Name
SACSCOC Approval obtained? | Name

## Academics Module
Task | Process Owner | Deliverable | Timeline
School
Develop/confirm curriculum | Dean | Documented in catalog & to website
Confirm course delivery format meets Wesleyan distance education standards | Dean/Director of CETL | Confirmed & documented by CETL
Confirm faculty distance education training needs | Dean/Director of CETL | Confirmed & documented by CETL
Define admissions criteria | Dean | Documented in catalog & posted to website
Develop/confirm class policies and academic standards | Dean | Documented in catalog & to website & communicated at orientation
Curriculum Management & Setup
Create/confirm academic calendar and dates | Dean/Registrar/IT | Academic Calendar; updated on web
Create schedule for posting classes and scheduling | Dean, Registrar | Meetings held, planned and determined
Create course sections | Dean/Registrar | In RamLink; Identify labeling to pull into website with Digital Marketing team
Assign faculty to courses | Dean/Registrar | In RamLink
Placement exams & Developmental Programs or related/similar requirements at graduate level depending on program
Determine need and process for administering placement exams | Senior Director of Academic Advising & Student Success/Director of Developmental Programs | Documented.
Determine communication with students related to placement test requirements, testing, results | Senior Director of Academic Advising & Student Success | Documented and on website
Determine developmental courses required, offerings, implementation, staffing, DL training | Director of Developmental Programs/Provost Office | Documented, plan implemented
Determine developmental supplemental instruction and tutoring support delivery | Director of Developmental Programs/Provost Office | Documented, plan implemented
Advising
Define advising process | Dean, Academic Advising (for UG) | Documented & on website & communicated at orientation
Determine access to/availability of advisors | Dean, Academic Advising (for UG) | Documented & on website & communicated at orientation
Registration
Create process for registering the student for the first time | Dean, Academic Advising (for UG)/Admission (for G), Registrar | Decision made, communicated at orientation/Website
Create process for all other registrations | Dean, Academic Advising (for UG), Registrar | Decision made, communicated at orientation/Website
Official transcript evaluation | Registrar/Admission | Process defined
Orientation
Develop timing for orientation | VP Student Affairs, New Student Programs, and participant areas (Academic Advising, Financial Aid, Cashier, Admission), Dean | Format & timing determined & documented
Create related components | VP Student Affairs, New Student Programs, and participant areas (Academic Advising, Financial Aid, Cashier, Admission), Dean | Orientation plan documented
Dropping, Withdrawing & Deregistering
Create process for adding/dropping classes | Registrar/ Dean | Documented and posted to website
Create process for withdrawing from program & University | Registrar/Business Office | Documented and posted to website
Create process for deregistering for nonpayment | Registrar/Business Office | Documented and posted to website
Policy confirmation, publication, implementation
Review all Catalog and Student Handbook policies and processes relevant to program; update each as needed to ensure applicability; ensure student remote access. | Registrar/Provost Office | Processes confirmed, updated as required and published; forms and procedures made accessible to students.
IT Student Support
Determine minimum technology requirements of students | Dean, IT User Services
Create standards for availability and support availability | IT User Services | Documented and posted to website
Create process for logging and handling support | IT User Services | Documented and posted to website
Create pre-testing for system compatibility | IT User Services | Documented and posted to website
Provide end-user support | IT User Services | Documented and posted to website
Provide Blackboard learning training & support | IT Applications | Documented process and posted to website
Commencement
Define process for confirming and communicating graduation | Registrar/Provost Office | Documented and posted to website
Create process for commencement | Registrar/Provost Office | Documented and posted to website
Determine if graduation will be on-campus or in-person, Diploma will be mailed or not | Registrar/Provost Office | Documented and posted to website

## Admissions & Adm. Services
Task | Process Owner | Deliverable | Timeline
Prospect Follow-up
Create process for phone calls and text messages | AVP Admission/Admission Director | Written process (ideally documented in Confluence)
Define departments responsible for answering specific questions | AVP Admission/Admission Director | Decision made and departments informed
Process for on-campus visits and questions | AVP Admission/Admission Director | Written process (ideally documented in Confluence)
Admissions Application Process
Define application/admission process | AVP Admission/Admission Director/Dean & Program director if Grad program/AVP Marketing | Process documented & on website.
Define file evaluation process | AVP Admission/Admission Director/Dean & Program director if Grad program | Written process (ideally documented in Confluence), team members trained
Set standards for turnaround decision | AVP Admission/Admission Director/Dean & Program director if Grad program | SME defined and trained
Create admissions decision process | AVP Admission/Admission Director/Dean & Program director if Grad program | Written process (ideally documented in Confluence), team members trained
Create username login credentials | AVP Admission/Admission Director | Define responsible person
Process to communicate credentials | AVP Admission/Admission Director | Integration into communications plans
Admissions Training
Develop or acquire program knowledge training | AVP Admission/Admission Director/Dean & Program director if Grad program | Meetings held with academics/key selling points defined
Develop or acquire customer service training | AVP Admission/Admission Director/Dean & Program director if Grad program | Documented process.
Designate and train strategic partnerships subject matter expert | AVP Admission/Admission Director/Dean & Program director if Grad program | SME defined and trained
Financial Aid
Develop financial aid policies for online students | Director Financial Aid/AVP Financial Services | Written and posted to website
Develop communication for financial aid requirements to students | Director Financial Aid/AVP Financial Services | Written emails and phone calls developed and documented & on website
Develop process for resubmitting FAFSA for returning students | Director Financial Aid/AVP Financial Services | Documented & on website
Designate and train strategic partnerships subject matter expert | Director Financial Aid/AVP Financial Services | Designated, documented and trained
Admitted Student Process
Define process for enrollment confirmation | AVP Admission/Director Admission/Registrar/Senior Dir. Acad Adv & Success (UG) or Dean (G) | Documented and posted to website
Define any other fees and processes for handling (like confirmation fees) | AVP Admission/Director Admission/Registrar/Senior Dir. Acad Adv & Success (UG) or Dean (G) | Documented and posted to website
Define process for hand-off to academics | AVP Admission/Director Admission/Registrar/Senior Dir. Acad Adv & Success (UG) or Dean (G) | Documented
Payment & Billing
Determine tuition & fees | VP Finance & Administration | Documented & posted to website
Define application fees and processing | AVP Financial Services/Student Accounts Manager | Documented and posted to website
Determine whether new "billing code" or rate is required | AVP Financial Services/Student Accounts Manager | Documented
Determine whether and how block rate may be affected | AVP Financial Services/Student Accounts Manager/IT/Admission | Documented
Define billing process (including dates) | AVP Financial Services/Student Accounts Manager | Documented and posted to website.
Third party/sponsor billing | AVP Financial Services/Student Accounts Manager | Documented and posted to website.
Develop communication for billing and payment process | AVP Financial Services/Student Accounts Manager | Documented; Emails created and live
Create communication (e.g. email) flow for payment due and de-registration warning | AVP Financial Services/Student Accounts Manager | Documented; Emails created and live
Create confirmation for successful payment | AVP Financial Services/Student Accounts Manager | Documented; Confirmation email and page created
Create Sql reports for tracking de-reg process | IT | Reports created
Customer service training and policies | AVP Financial Services/Student Accounts Manager | Documented and posted to website; sub-meetings held
Create payment and billing processes for returning students | AVP Financial Services/Student Accounts Manager | Documented & posted to website
Alumni Development
Create promotional process, information, materials. | Alumni Director | Process and materials developed.
Create processes for capturing student information | Alumni Director | Process documented.
Continuous engagement plan | Alumni Director | Documented
Continuous Improvement
Develop customer service metrics, measurements and tools | Associate Provost for Academic Policy and Support/Accreditation Liaison/All areas | Process, expected outcomes confirmed and documented.

## Marketing Module
Task | Process Owner | Deliverable | Timeline
Advertising & Awareness
Concept and create broadcast marketing | AVP Marketing & Communications | Google AdWords, Facebook, YouTube
Inquiry generation, communications strategies & tracking | AVP Marketing & Communications | Communications plans & follow-up communications
Launch landing pages, web pages and digital video | Director of Digital Marketing & Strategy | Landing pages, web pages and digital video
Form strategic partnerships | Director of Strategic Partnerships | Signed MOUs and Partnership Recommendations
Conversion
Launch program applications | Director of Admission Operations | Program application iterations
Reporting
Follow-up plan | AVP Marketing & Communications | Regular meetings and feedback
Metrics cycle | AVP Marketing & Communications | Inquiry and enrollment reports

## Student Support
Task | Process Owner | Deliverable | Timeline
Faculty/Advisor Support
Define type of support needed/anticipated related to in-course progress & performance | Dean | Decision made & documented
Define type of support needed/anticipated related to program progress, post-program plans and other mentoring expectations | Dean | Decision made & documented
Determine who should provide this support | Dean | Decision made & documented
Determine student access to support (how and when) | Dean | Decision made & documented & explained at orientation & on website
Create assessment plan | Dean | Assessment plan made
Library
Determine library support needs and whether anything special/additional | Dean & Director of West Library | Decision made & documented
Determine where/how students will access (directly through library website, dedicated web page, portal, etc.) | Director of West Library | Decision made & documented & explained at orientation & on website
Determine student training requirements & student access | Director of West Library | Decision made & documented & explained at orientation & on website
Create assessment plan | Director of West Library | Assessment plan made
Career Services
Confirm whether students need usual career support services or anything additional or special | Director of Career Services, Dean | Decision made & documented
Determine job placement opportunities/needs | Director of Career Services, Dean | Documented and posted to website
Determine type of student access to information and services. Online, by telephone, etc. and how/where/when | Director of Career Services, Dean | Decision made & documented & explained at orientation & on website
Tutuoring & Study Skills Support
Detemine type of support needed, e.g. writing support, quantitative skills support, other subject tutoring, study skills | Dean & Senior Director of Academic Advising and Support | Decision made & documented
Determine who will provide support and determine staffing needs | Dean & Senior Director of Academic Advising and Support | Decision made and documented
Determine student access to support (how and when) | Dean & Senior Director of Academic Advising and Support | Decision made and documented & explained at orientation & on website
Determine how to identify Distance Learning (DL) students who need academic assistance and how we intervene to provide them assistance | Dean & Senior Director of Academic Advising and Support | Decision made and documented
Create assessment plan |  | Assessment plan made
Personal Counseling
Confirmation potential residensce of students; Determine type of student access. Online by telephone, etc. and how/where/when | Director of Counseling | Decision made & documented & explained at orientation & on website
Determine staffing needs | Director of Counseling | Decision made & documented
Create assessment plan | Director of Counseling | Assessment plan made
Disability Services
Determine access to services & communication with student and faculty | Director of Disability Services/Assoc. Provost Acad. Aff. | Decision made and documented & explained at orientation & on website
Student Engagement
Determine appropriate student engagement (student life) activities | Dean & VP for Student Affairs | Decisions made and documented. Posted to website/provided in orientation as appropriate.
Determine need for co-curriculum/extracurricular opportunities. Organizations, presentations? | Dean & VP for Student Affairs | Decisions made and documented. Posted to website/provided in orientation as appropriate.
Discuss other support needs or referrals. What is customary for distance education programs such as this one? | Dean & VP for Student Affairs | Decisions made and documented. Posted to website/provided in orientation as appropriate.
Review and confirm Student Handbook policies to ensure applicability and access. | VP for Student Affairs | Decisions made and documented. Posted to website/provided in orientation as appropriate.
Once student engagement and other support determined, determine student access, communication, staffing. | Dean & VP for Student Affairs | Document. Post to website, include in orientation, etc.
Alumni support
Determine engagement and support while students are enrolled and post-graduation. | Alumni Director | Decision made and documented. Outreach made, posted on website as appropriate.
Student Complaint Procedures and Processes
Confirm and make clear DL process for students who wish to pursue any complaint process. (Access to policies, forms, individuals) | Associate Provost for Academic Policy & Support/Accreditation Liaison | Decision made and documented & posted to website